Celebrate Fremont

Fundraising Committee Minutes

Of August 22, 2005

Attendees: (X Denotes Present)

| X | Jack Rogers |  | Les Mensinger |
| --- | --- | --- | --- |
|  | Sue Chan | X | Sally Buonomo |
| X | Mike King | X | Bob Creveling |
|  | Biff Butler |  | Gene Anderson |
| X | Salim Mastan | X | Laura Eagan |
| X | Adele Jaimes | X | Bill Eagan |
| X | Steve Cho |  | Taskeen Fatehdin |
| X | Gaby Machuca (guest) | X | Irene Koehler (guest) |

Minutes

Introductions made

Mike: - Almost all data necessary to be in Exceed has been input - Needs to evolve Exceed further such as: Ways to follow up, extracting data etc. - Catellus info in Exceed is current - Continue x-training Geraldine on software - Pledge cards and brochures are complete - Premier Pizza is working on technical stuff for PowerPoint presentation

Bill/Laura: - Almost all of the donations from Massimo’s are in - Call list to Catellus invitees needs to be completed by Friday - Seems like not too many of the invitations to Catellus receptions were received - Next Community Meeting is Sept. 15, 2005, @ Center Theater - Brochure has been completed by Doug Tinney and is going to be sent to all invitees - Focus is to raise “People Power” To round up more volunteers

Gaby: - The Business & Neighborhood team have a "passport" concept and would like to proceed in soliciting "prizes" from within Fremont and outside of Fremont - “Passport" will engage Fremont Community members to discover Fremont. It will be a type of game each participant will have a passport with he names of local business from throughout the Fremont Districts. The more places the participant visits and receives a stamp from the better his/her prize level entry goes up. The idea is that we hope that by offering "huge" prizes for completing the passport and culminating at the Celebration @ The Park on Sept 9 7 10 , 2006. Gather prizes will be available for those who participants and who visit 1/2 or 1/3 of the locations on the passport - Different teams from Celebrate Fremont should not solicit from the same folks. * - Their needs to be a plan in place* - Who will write the donation letter?* - Who will the donation letter be sent to?* - Will the participants (on the “Passport”) be charged a fee?*

Steve: - Proposal for 50/50 Raffle - Who will sell tickets? - Data entry for each ticket to be done - To be proposed at SC*

Irene: - Geraldine has been hired to replace Sally, as Sally will be starting school on a full-time basis. - Thank you should be sent to Syntec for donations of PC’s

Jack: - A committee needs to be established by the SC to be a clearing house for donations as not to solicit the same people * - Need to co-ordinate a donation letter* - Next meeting is 9-7-05 - Most of the Thank You letters for Massimo’s Dinner have gone out - Markus of Catellus sent RSVP update

* Action Items developed

Action Items

| ID | Open Date | Description | Assigned to | Target Date | Date Closed |
| --- | --- | --- | --- | --- | --- |
| 13 | 6-6-05 | Find out if the Boy Scouts are interested in doing a sporting event with us. | To be assigned | TBD |  |
| 15 | 6-6 | look into donations by community groups (names of clubs needed) See AI # 19 Present to various clubs regarding commitment to raise money$ for CF (with AI # 15) to be assigned to Joint-Subcommittee | Gene Anderson & Les | 7-25-05 8-8-05 9-19-05 |  |
| 16 | 6-6 | Contact PGE, Alameda County Water and BFI and Comcast so enclose information about CF in their mailings or on their TV channel. Discussion was held (7-25-05) to have companies send information as inserts in with their billing. | Bill | 7-25-05 8-08-05 9-19-05 |  |
| 17 | 6-6 | Look into school bake and notify Salim about looking into “50/50 Salim to contact Moina On Education Team | Taskeen & Salim | 7-25-05 8-8-05 8-22-05 9-18-05 |  |
| 26 | 6-30 | Approach Rotary Clubs and “pitch” CF to new incoming presidents | Bill and Mayor Bob | 7-25-05 10-03-05 |  |
| 27 | 7-11 | Look into cost of programs would cost should we decide to hand them out at the Sept. celebration. | Jack | 8-8-05 8-22-05 | 8-22-05 |
| 32 | 8-8 | Send e-mail RSVPs to Catellus Reception to Sally | Laura | Thru 9-5-05 |  |
| 33 | 8-8 | Follow up on names that did not have addresses from list Salim gave to Catellus Reception | Salim | 8-29-05 9-7-05 |  |
| 34 | 8-8 | Call Exceed Support regarding the different events of CF. How to better utilize system | Sally | 8-22-05 | 8-22-05 |
| 35 | 8-8 | - Check donation list as to who has been invoiced - Check who has been invoiced and follow up - Generate invoice process | Mike | Ongoing thru 10-03-05 | 8-22-05 |
| 36 | 8-8 | Enter a “Send Packet” column to Exceed list | Sally | 8-22-05 | 8-22-05 |
| 39 | 8-8 | Send follow up responses regarding donations to Sally | Sue, Bill | 8-22-05 9-15-05 |  |
| 40 | 8-8 | Discuss with Jack how to incorporate Salim’s Action Plan regarding calls to businesses and households | Bill and Laura | 8-22-05 | 8-22-05 |
| 41 | 8-8 | Set up50/50 Raffle | Steve | 8-22-05 | 8-22-05 |
| 42 | 8-22 | Sub-Committee to be set up to further develop 50/50 raffle after SC Approval | Jack | 9-7-05 To be added to FRC agenda |  |
| 43 | 8-22 | Make proposal to Steering Committee regarding 50/50 raffle | Jack | 8-31-08 |  |
| 44 | 8-22 | Propose to SC the need to establish a clearing house for donations as not to solicit the same people. A member of the FRC will also sit on this newly established sub-committee. Also a donation letter needs to be developed | Laura/Irene | 8-31-05 |  |

Next Meeting

| Date: | Sept. 7, 2005, Wednesday |
| --- | --- |
| Time: | 6:45 p.m. – 8:30 p.m. |
| Location: | CF Office on Eggers |
| Facilitator: | Jack Rogers |
| Scribe: | Adele Jaimes |