Celebrate Fremont

Fundraising Committee Minutes

August 8, 2005

Attendees: (X Denotes Present)

|  | Jack Rogers |  | Les Mensinger |
| --- | --- | --- | --- |
| X | Sue Chan | X | Sally Buonomo |
| X | Mike King |  | Bob Creveling |
|  | Biff Butler | X | Gene Anderson |
| X | Salim Mastan | X | Laura Eagan |
| X | Adele Jaimes | X | Bill Eagan |
| X | Steve Cho |  | Taskeen Fatehdin |

Minutes (14)

Bill: - Invites to Catellus reception were mailed. No RSVPs as of yet - RSVPs to be tracked on Exceed - To follow up with phone calls to invitees regarding the reception - To follow up with invitees who have not RSVP by Sept. 5th date - Will assign members who know the contacts to make calls. The rest will be assigned to others - Will not have to contact Catellus prospects - Volunteers for calls are; Sally , Steve, Bill, Laura, Mike, Gene and Adele

Mike: - Exceed will have a new upgrade in September - Exceed can only be open on one PC at a time - At this time CF has only one license - At this time only Sally, Mike and Jack know the Exceed software. A possibility to train others

Round Table Report Sue: - Is there a process to follow up on the Massimo’s donors? - Follow up needs to be at 30 day cycles - Also need a tracking process Bill: - Some invitees would like to have a handout to prior to the Sept.12th reception - Sally will add “Send Packet” to the Exceed program Steve: - Some of his follow up calls stated they are waiting for managers to approve donations - Some stated no donations - Others need to wait and see Salim: - Submitted his Action Plan on calling smaller businesses and household of 70,000 - A script will need to be developed - Bill and Laura will discuss with Jack how to incorporate at the Community meeting - Will be discussed at Steering Committee meeting on Wednesday - Will need to make a list of needs regarding volunteering to assist with CF prior to calls

Minutes Con’t

Sally’s Transition: - Sally’s internship will end on August 23rd - CF will take application for another intern - CF needs to staff office with someone who can be there on regular basis - There is a possibility of getting a paid staff Sally stated she will still assist with the Catellus Reception. Everyone expressed that Sally will be truly missed. Not only for her great abilities, but as a friend. She stated she has made very good friend and still wants to be part of CF.

Action Items

| ID | Open Date | Description | Assigned to | Target Date | Date Closed |
| --- | --- | --- | --- | --- | --- |
| 13 | 6-6-05 | Find out if the Boy Scouts are interested in doing a sporting event with us. | To be assigned | TBD |  |
| 15 | 6-6 | look into donations by community groups (names of clubs needed) See AI # 19 Present to various clubs regarding commitment to raise money$ for CF (with AI # 15) to be assigned to Joint-Subcommittee | Gene Anderson & Les | 7-25-05 8-8-05 8-22-05 |  |
| 16 | 6-6 | Contact PGE, Alameda County Water and BFI and Comcast so enclose information about CF in their mailings or on their TV channel. Discussion was held (7-25-05) to have companies send information as inserts in with their billing. | Bill | 7-25-05 8-08-05 |  |
| 17 | 6-6 | Look into school bake and notify Salim about looking into “50/50 Salim to contact Moina On Education Team | Taskeen & Salim | 7-25-05 8-8-05 8-22-05 |  |
| 26 | 6-30 | Approach Rotary Clubs and “pitch” CF to new incoming presidents | Bill and Mayor Bob | 7-25-05 10-03-05 |  |
| 27 | 7-11 | Jack will look into how much programs would cost should we decide to hand them out at the Sept. celebration. | Jack | 8-8-05 8-22-05 |  |
| 29 | 7-25 | Develop and Action Plan, Budget and a To Do List with milestones regarding calls to other businesses and households (70,000) | Salim | 8-08-05 | 8-08-05 |
| 30 | 7-25 | Set up Excel Spread Sheet with donors given by Salim. Email to Salim and cc Jack | Adele | 7-25-05 | 7-25-05 |
| 31 | 7-25 | Compete Excel sent by Adele with names of Contacts, Addresses and Phone #’s | Salim | 7-29-05 | 7-29-05 |
| 32 | 8-8 | Send e-mail RSVPs to Catellus Reception to Sally | Laura | Thru 9-5-05 |  |
| 33 | 8-8 | Follow up on names that did not have addresses from list Salim gave to Catellus Reception | Salim | 8-29-05 |  |
| 34 | 8-8 | Call Exceed Support regarding the different events of CF. How to better utilize system | Sally | 8-22-05 |  |
| 35 | 8-8 | - Check donation list as to who has been invoiced - Check who has been invoiced and follow up - Generate invoice process | Mike | Ongoing thru 10-03-05 |  |
| 36 | 8-8 | Enter a “Send Packet” column to Exceed list | Sally | 8-22-05 |  |
| 39 | 8-8 | Send follow up responses regarding donations to Sally | Steve, Sue, Bill | 8-22-05 |  |
| 40 | 8-8 | Discuss with Jack how to incorporate Salim’s Action Plan regarding calls to businesses and households | Bill and Laura | 8-22-05 |  |
| 41 | 8-8 | Set up50/50 Raffle | Steve | ? |  |

Next Meeting

| Date: | TBD |
| --- | --- |
| Time: | 6:45 p.m. – 8:30 p.m. |
| Location: | CF Office on Eggers |
| Facilitator: | Jack Rogers |
| Scribe: | Adele Jaimes |