Celebrate Fremont

Fundraising Committee Minutes/Action Items

June 30, 2005

Attendees: (X Denotes Present)

| X | Jack Rogers | X | Les Mensinger |
| --- | --- | --- | --- |
| X | Sue Chan | X | Sally Buonomo |
| X | Mike King | X | Bob Creveling |
|  | Biff Butler |  | Gene Anderson |
|  | Salim | X | Laura Eagan |
| X | Adele Jaimes | X | Bill Eagan |
|  | Taskeen Fatehdin |  |  |

Minutes

Introductions were not necessary

Sue: Fundraising Dinner of June 27th at Massimo’s: - Was a SMASHING SUCCESS- over 500K in cash and in-kind donated - Everyone worked very hard - Many Lessons Learned for next event to run even more smoothly Next Event: Dan Marcus of Catellus will set up with Sue to the possible use of an empty building @ Pacific Commons: - Develop a list of the next tier of businesses in Fremont - Need to know capacity to determine how many to invite Some businesses will want Tax ID, W-9 and/or Donation Letters. Sue will FAX these to those businesses who request

Mike: - Put up donation page on to CF website - The charge will be $30 per month - 1st 30 days was free, CF paid for 3 months after - Fremont Bank is waiving all of their charges

Jack and Bill: - To have a Fundraising booth at the 2-day event. To be tabled until spring of next year - Per Bill, Steve Cho stated CF will be able to put 4 cash boxes at bank - Adele will not be at next meeting. Will ask Sally if she would take minutes

Celebrate Fremont

Fundraising Committee Minutes/Action Items con’t

June 6, 2005

Action Items

| ID | Open Date | Description | Assigned to | Target Date | Date Closed |
| --- | --- | --- | --- | --- | --- |
| 13 | 6-6-05 | Find out if the Boy Scouts are interested in doing a sporting event with us. | Biff | 6-23-00 7-25-05 |  |
| 14 | 6-6 | Ask Steve Cho to look into information on cash box donations. (still to look into) | Mike King | 6-23-00 7-25-05 |  |
| 15 | 6-6 | look into donations by community groups (names of clubs needed) See AI # 19 | Gene Anderson & Les | 6-23-00 7-25-05 |  |
| 16 | 6-6 | Contact PGE, Alameda County Water and BFI and Comcast so enclose information about CF in their mailings or on their TV channel. | Bill | 6-23-00 7-25-05 |  |
| 17 | 6-6 | look into school bake and notify Salim about looking into “50/50 and solicit money from school children.” | Taskeen | 6-23-00 7-25-05 |  |
| 19 | 6-23 | Present to various clubs regarding commitment to raise money$ for CF (with AI # 15) | Gene Anderson & Les | 7-25-05 |  |
| 20 | 6-23 | Get together with Lisa regarding setting up a place on CF website where folks are able to donate cash | Mike | 6-30-05 | 6-30-05 |
| 21 | 6-23 | Update FR roster after the dinner | Adele and Jack | 6-30-05 | 6-30-05 |
| 22 | 6-30 | Donation information to be put on CF website | Sue | 7-25-05 |  |
| 23 | 6-30 | Enter information on website regarding the security of making donation | Mike | 7-25-05 |  |
| 24 | 6-30 | Develop budget for FR Committee and send to Thomas | Jack | 7-25-05 |  |
| 25 | 6-30 | Follow up on Pledges, and Businesses not yet pledged but attended dinner | Laura | 7-25-05 |  |
| 26 | 6-30 | Approach Rotary Clubs and “pitch” CF to new incoming presidents | Bill and Mayor Bob | 7-25-05 |  |

Celebrate Fremont

Fundraising Committee Minutes/Action Items Continued

June 23, 2005

Next Meeting

| Date: | July 25, 2005 |
| --- | --- |
| Time: | 7 p.m. – 8:30 p.m. |
| Location: | CF Office on Eggers |
| Facilitator: | Jack Rogers |
| Scribe: | Sally Buonomo |