Celebrate Fremont

Fundraising Committee Minutes/Action Items

June 6, 2005

Attendees: (X Denotes Present)

| X | Jack Rogers |  | Taskeen Fatehdin |
| --- | --- | --- | --- |
| X | Sue Chan | X | Les Mensinger |
| X | Mike King | X | Laura Eagan |
| X | Biff Butler | X | Sally Buonomo |

Minutes

Jack: - Ran through minutes from the May 24 meeting. - Assigned action item number 8 of last minutes to Mike King. - Asked Sally to formulate a roster that also contains addresses and phone numbers. - Jack requested that we add introductions as a standard item at all meetings. - Met 2 people who are seeking to become fundraising committee members

Sue: - Reported that 80 invitations had been sent and an additional 60. - Received 9 RSVPs representing; 13 seats have responded and 1 decline thus far. - Follow phone calls (informational) will be made by the Mayor and the 4 city council members. Should be completed by Wednesday. - Sue asked Laura to bring a copy of the invite to the next meeting. - If we meet our capacity then we will have to offer then a seat in a future activity. - Working on an agenda, electronic presentation (Doug Tinney), a program and a folder of presentation material are being developed for the June 27th meeting.

Mike: - Established a website for Fundraising committee members contact information - Requested that if a RSVP comes in a e-mail to him would be appreciated.

Grouping of Brainstorming Suggestions:

- Sport activities: Triathlon, Walk-a-thon, Bike rally, Golf Tourney

- Mail Campaign: Email, direct and targeted, donation set-up on website

- Naming rights to activity: Bricks, band shell

- Food: Bake sales, vendor set up at event itself, progressive dinner, Historic dinner, Crab feed

- Donation: Merchandise, information booth, wristband

- Auction: White elephant, silent, celebrity, raffle

Action Items

| ID | Open Date | Description | Assigned to | Target Date | Date Closed |
| --- | --- | --- | --- | --- | --- |
| 13 | 6-6 | Find out if the Boy Scouts are interested in doing a sporting event with us. | Biff | 6-23-00 |  |
| 14 | 6-6 | Ask Steve Cho to look into information on cash box donations. | Mike King | 6-23-00 |  |
| 15 | 6-6 | look into donations by community groups | Gene Anderson & Les | 6-23-00 |  |
| 16 | 6-6 | contact PGE, Alameda County Water and BFI and Comcast so enclose information about CF in their mailings or on their TV channel. | Bill | 6-23-00 |  |
| 17 | 6-6 | look into school bake and notify Salim about looking into “50/50 and solicit money from school children.” | Taskeen | 6-23-00 |  |
| 18 | 6-6 | look into how to work donations at Art and Wine Festivals | Bob | 6-23-00 |  |

Next Meeting

| Date: | June 23, 2005 |
| --- | --- |
| Time: | 7 p.m. – 8:30 p.m. |
| Location: | CF Office on Eggers |
| Facilitator: | Jack Rogers |
| Scribe: | Adele Jaimes |